## User Guide & Vetting Guide
C SYSTEMS PROGRAMMING 45-DAY ELITE FAST-TRACK - GUIDE & METRICS
1. HOW TO NAVIGATE AND FILL THE TRACKER
Action Step | Procedural Instructions & Methodology | Associated Tab / Location
Step 1: Read Daily Spec | Go to your workspace folder: /c-fast-track/Day_Plans/. Read the corresponding daily blueprint (Day_01.md to Day_45.md). Read the 4-Hour Theory Deep-Dive and complete the 4-Hour Unassisted Lab. | Workspace Files: Day_Plans/
Step 2: Update Progress Status | Select the 'Daily Progress Tracker' worksheet tab in this workbook. Locate the current day and set the 'Status' column dropdown selector to 'In Progress' or 'Completed'. | Tab 3: Daily Progress Tracker
Step 3: Audit & Grade Task | Once the lab compiles and executes with zero warning flags, evaluate your understanding against the 5-Tier Vetting Scale. Select the appropriate rating from the 'Grade / Audit' column dropdown list. | Tab 3: Daily Progress Tracker
Step 4: Analyze Dashboard | Switch to the 'Executive Dashboard' worksheet tab. Analyze real-time KPI metrics cards and track active phase completion progress displayed on the column charts. | Tab 2: Executive Dashboard
2. 5-TIER UNDERSTANDING MEASUREMENT METRICS (VETTING CRITERIA)
Grade / Audit Score | Scale Target % | Physical Evaluation Benchmarks (MISRA C & Hardware Vetting Standards)
A+ [100%] | 100% | Perfect unassisted delivery. Zero compiler warnings under strict '-Wall -Wextra -Werror -pedantic' C11 constraints. No memory leaks detected under Valgrind. Registers and hardware metrics successfully audited via GDB/Logic Analyzer.
A [90%] | 90% | Clean compilation and execution with zero compiler warnings. Minor assisted code style adjustments permitted. High-quality documentation and safe defensive pointer boundaries implemented successfully.
B [80%] | 80% | Compiles cleanly. Minor assisted corrections needed during structural alignments or preprocessor macros expansions. Program achieves functional output targets under debug audits.
C [70%] | 70% | Compiles and runs with helper hints during lab execution. Program is functional, but contains suboptimal branching choices, redundant loops, or unoptimized variables structures.
F [Fail] | 0% | Program fails to compile cleanly, contains memory leaks under Valgrind, or fails to implement basic functional registers validation gates.
Pending | - | Day task is not yet started or has not been audited.
3. KEY MILESTONE GATING CHECKS
Phase | Days Mapped | Core Gating Challenge Target
Phase 1: Compiler & Toolchains | Days 01 - 05 | Build modular project compiled with MM/MMD incremental Make dependency tracking.
Phase 2: Data & Radix Hazards | Days 06 - 10 | Write branch-free absolute value/conditional select routines checking asm loops.
Phase 3: Stack & Execution Frame | Days 11 - 15 | SMASH stack buffer of a dummy string array verifying stack canaries trap hook.
Phase 4: Pointers & Arithmetic | Days 16 - 20 | Implement command processor jump-table routing calculations cleanly without switch constructs.
Phase 5: Structures & Alignments | Days 21 - 25 | Manually serialize structural elements into Big-Endian arrays for network transport.
Phase 6: Custom Allocators | Days 26 - 30 | Write custom aligned linear Arena and O(1) Slab allocator free list.
Phase 7: POSIX System Boundaries | Days 31 - 35 | Configure zero-copy shared database mapper file index utilizing POSIX mmap.
Phase 8: Preprocessor Metaprogramming | Days 36 - 40 | Generate dynamic Enum lists and translate functions using X-Macros tables.
Phase 9: Concurrency & MISRA C | Days 41 - 45 | Create thread-safe Producer-Consumer ring buffer using POSIX mutexes and cond variables.

## Executive Dashboard
C SYSTEMS PROGRAMMING EXECUTIVE DASHBOARD
TOTAL TARGET DAYS |  | COMPLETED | IN PROGRESS | NOT STARTED | OVERALL COMPLETION %
45
TRAINING PHASE PERFORMANCE HIGHLIGHTS
Phase / Module Name | Days Included | Status | Completion % | Milestone Target Gate
Phase 1: Compiler & Toolchains | Day 01 - 05 |  |  | Makefile Dependency Hook
Phase 2: Data & Radix Hazards | Day 06 - 10 |  |  | Safe Float-Compare Parser
Phase 3: Stack & Execution Frame | Day 11 - 15 |  |  | Stack Canary Overflow Audit
Phase 4: Pointers & Arithmetic | Day 16 - 20 |  |  | Jump-Table Callbacks Map
Phase 5: Structures & Alignments | Day 21 - 25 |  |  | Serialized Pack/Unpack
Phase 6: Custom Allocators | Day 26 - 30 |  |  | O(1) Slab Allocator
Phase 7: POSIX System Boundaries | Day 31 - 35 |  |  | Memory-Mapped Database Engine
Phase 8: Preprocessor Metaprogramming | Day 36 - 40 |  |  | X-Macros Dynamic Lookup Table
Phase 9: Concurrency & MISRA C | Day 41 - 45 |  |  | MISRA pthreads Scheduler
Overall Program Status | 45 Days |  |  | Final Graduation

## Daily Progress Tracker
C SYSTEMS PROGRAMMING ELITE 45-DAY FAST-TRACK
Day | Phase | Core Focus Topic | Vetting Challenge Task | Target Date | Status | Weight | Grade / Audit | Notes / Blockages
Day 01 | Phase 1: Compiler & Toolchains | The Preprocessor Pipeline and Macro Expansion Hazards | Compile and audit square preprocessor macros side-effects output | 2026-06-01 | Completed | 2.222% | A+ [100%] | Passed Autovet Harness on 2026-05-30 11:14
Day 02 | Phase 1: Compiler & Toolchains | Compilation to Assembly and GDB Register Analysis | Compile to assembly using -S and step through execution registers | 2026-06-02 | Not Started | 2.222% | Pending
Day 03 | Phase 1: Compiler & Toolchains | Relocatable Object Files Dissection and Symbol Resolution | Dissect symbols and segments (.text, .data, .bss, .rodata) using nm | 2026-06-03 | Not Started | 2.222% | Pending
Day 04 | Phase 1: Compiler & Toolchains | Linking Mechanics, Static/Dynamic Libraries, and Symbol Collisions | Compile and link dynamic libraries checking rpath | 2026-06-04 | Not Started | 2.222% | Pending
Day 05 | Phase 1: Compiler & Toolchains | GNU Make, Implicit Dependencies, and Incremental Builds | Write self-dependency tracking Makefile with MM/MMD | 2026-06-05 | Not Started | 2.222% | Pending
Day 06 | Phase 2: Data & Radix Hazards | POSIX Integer Scales, Two's Complement, and Sign Extensions | Assign signed variables to unsigned variables printing raw hexadecimal | 2026-06-08 | Not Started | 2.222% | Pending
Day 07 | Phase 2: Data & Radix Hazards | Safe Integer Arithmetic, Overflow Detection, and Type Promotions | Write robust overflow pre-check addition/multiplication C functions | 2026-06-09 | Not Started | 2.222% | Pending
Day 08 | Phase 2: Data & Radix Hazards | Floating-Point Internals (IEEE 754) and Precision Hazards | Write robust epsilon float equality comparison logic | 2026-06-10 | Not Started | 2.222% | Pending
Day 09 | Phase 2: Data & Radix Hazards | Bitwise Operations, Masking, and Shift Hazards | Design register status flags bit togglers avoiding undefined shifts | 2026-06-11 | Not Started | 2.222% | Pending
Day 10 | Phase 2: Data & Radix Hazards | Branch-Free Programming and ALU Pipeline Optimization | Write branch-free absolute value and select methods checking assembly | 2026-06-12 | Not Started | 2.222% | Pending
Day 11 | Phase 3: Stack & Execution Frame | Activation Records and Procedure Call Standards (AAPCS) | Verify AAPCS register arguments passing in GDB breakpoints | 2026-06-15 | Not Started | 2.222% | Pending
Day 12 | Phase 3: Stack & Execution Frame | Function Frame Layout, Prologue, and Epilogue Assembly | Audit SP moves and push/pop instruction layouts inside custom assembly | 2026-06-16 | Not Started | 2.222% | Pending
Day 13 | Phase 3: Stack & Execution Frame | Local Variable Lifetimes, Storage Classes, and Scope Boundaries | Verify static address persistence vs stack decay warnings | 2026-06-17 | Not Started | 2.222% | Pending
Day 14 | Phase 3: Stack & Execution Frame | Stack Overflow Hazards, MSP vs PSP, and MPU Guard Bands | Generate stack overflows in GDB using recursive allocations | 2026-06-18 | Not Started | 2.222% | Pending
Day 15 | Phase 3: Stack & Execution Frame | Stack Canaries and Buffer Overflow Defensive Coding | Verify stack protector failure trap hook by smashing local buffer | 2026-06-19 | Not Started | 2.222% | Pending
Day 16 | Phase 4: Pointers & Arithmetic | Pointers Dereferencing, Decay, and Multi-Dimensional Arrays | Write row-major calculations representing matrix offsets | 2026-06-22 | Not Started | 2.222% | Pending
Day 17 | Phase 4: Pointers & Arithmetic | Pointer Arithmetic Scaling Mathematics and Offset Mapping | Verify address scaling gaps based on target types size differences | 2026-06-23 | Not Started | 2.222% | Pending
Day 18 | Phase 4: Pointers & Arithmetic | Volatile Pointer Configurations and Memory-Mapped Registers | Audit optimized assembly polling loops with and without volatile | 2026-06-24 | Not Started | 2.222% | Pending
Day 19 | Phase 4: Pointers & Arithmetic | Function Pointers, Callback Systems, and Jump-Tables | Implement calculator command jump-table eliminating switch logic | 2026-06-25 | Not Started | 2.222% | Pending
Day 20 | Phase 4: Pointers & Arithmetic | Raw Pointer Casting, Type Safety, and Alignment Validations | Design address checks tracking alignment gaps before pointer writes | 2026-06-26 | Not Started | 2.222% | Pending
Day 21 | Phase 5: Structures & Alignments | Structure Memory Layouts, Compiler Padding, and Offset Tracing | Trace struct layout offsets to minimize padding size footprint | 2026-06-29 | Not Started | 2.222% | Pending
Day 22 | Phase 5: Structures & Alignments | Packed Structures, Alignment Pragma/Attributes, and Performance Costs | Analyze normal vs packed structures and assembly operations cost | 2026-06-30 | Not Started | 2.222% | Pending
Day 23 | Phase 5: Structures & Alignments | Unions, Type Punning, and Raw Binary Serialization | Inspect raw floating-point bits and serialize structs in unions | 2026-07-01 | Not Started | 2.222% | Pending
Day 24 | Phase 5: Structures & Alignments | Bitfields, Hardware Register Mapping, and Alignments | Define status register bitfields and audit compile mask calculations | 2026-07-02 | Not Started | 2.222% | Pending
Day 25 | Phase 5: Structures & Alignments | Network Serialization, Endianness, and Byte Order Conversion | Implement byte order serializer converting variables to Big-Endian | 2026-07-03 | Not Started | 2.222% | Pending
Day 26 | Phase 6: Custom Allocators | Dynamic Heap Architecture, Fragmentation, and System Boundaries | Verify heap break address adjustments using sbrk system calls | 2026-07-06 | Not Started | 2.222% | Pending
Day 27 | Phase 6: Custom Allocators | Custom Memory Arenas and Alignment Boundaries | Implement linear aligned arena allocator enforcing 8-byte boundaries | 2026-07-07 | Not Started | 2.222% | Pending
Day 28 | Phase 6: Custom Allocators | Fixed-Size Memory Block Pools | Implement deterministic O(1) free list block pool memory slab allocator | 2026-07-08 | Not Started | 2.222% | Pending
Day 29 | Phase 6: Custom Allocators | Dynamic Free Lists, Block Splitting, and Coalescing | Design first-fit block coalescing merging neighboring free headers | 2026-07-09 | Not Started | 2.222% | Pending
Day 30 | Phase 6: Custom Allocators | Memory Leaks Audits and Dynamic Wrapper Sentinels | Implement custom malloc/free wrapper tracking allocations leaks context | 2026-07-10 | Not Started | 2.222% | Pending
Day 31 | Phase 7: POSIX System Boundaries | System Call Boundaries and Unbuffered POSIX I/O | Write unbuffered file copier using open/read/write system calls | 2026-07-13 | Not Started | 2.222% | Pending
Day 32 | Phase 7: POSIX System Boundaries | Asynchronous I/O, Non-Blocking Descriptors, and Streaming | Configure pipe descriptors in O_NONBLOCK mode handling EAGAIN | 2026-07-14 | Not Started | 2.222% | Pending
Day 33 | Phase 7: POSIX System Boundaries | Memory-Mapped Files (mmap) and Zero-Copy I/O | Write database binary indexing editor using shared mmap maps | 2026-07-15 | Not Started | 2.222% | Pending
Day 34 | Phase 7: POSIX System Boundaries | System Error Handling, Thread-Safe errno, and Recovery | Implement thread-safe strerror_r system error logger | 2026-07-16 | Not Started | 2.222% | Pending
Day 35 | Phase 7: POSIX System Boundaries | Inter-Process Communication (IPC) and Shared Memory | Implement telemetry sender and receiver using POSIX shared memory | 2026-07-17 | Not Started | 2.222% | Pending
Day 36 | Phase 8: Preprocessor Metaprogramming | Preprocessor Extensions, Token Concatenation, and Stringification | Write dynamic variable builder and string logger macros | 2026-07-20 | Not Started | 2.222% | Pending
Day 37 | Phase 8: Preprocessor Metaprogramming | Multi-Line Macros Safety and do-while wrappers | Wrap macro operations in do-while structures to pass conditional parses | 2026-07-21 | Not Started | 2.222% | Pending
Day 38 | Phase 8: Preprocessor Metaprogramming | X-Macros Code Generation and Dynamic Lookups | Generate enum declarations and lookup strings from central X-Macro list | 2026-07-22 | Not Started | 2.222% | Pending
Day 39 | Phase 8: Preprocessor Metaprogramming | Variadic Macros and C11 _Generic Type Selections | Design generic abs macros routing floats/ints at compile-time | 2026-07-23 | Not Started | 2.222% | Pending
Day 40 | Phase 8: Preprocessor Metaprogramming | Include Guards, Conditional Compilations, and Assertions | Enforce compile-time data sizes constraints using C11 _Static_assert | 2026-07-24 | Not Started | 2.222% | Pending
Day 41 | Phase 9: Concurrency & MISRA C | POSIX Threads (pthreads) Creation, Joins, and Configurations | Spawn 4 worker pthreads executing concurrent jobs passing exits | 2026-07-27 | Not Started | 2.222% | Pending
Day 42 | Phase 9: Concurrency & MISRA C | Race Conditions, Mutex Locks, and Deadlock Avoidance | Audit counter racing under Helgrind and lock access using mutexes | 2026-07-28 | Not Started | 2.222% | Pending
Day 43 | Phase 9: Concurrency & MISRA C | Condition Variables and Producer-Consumer Buffers | Coordinate Producer-Consumer ring buffer utilizing pthreads cond variables | 2026-07-29 | Not Started | 2.222% | Pending
Day 44 | Phase 9: Concurrency & MISRA C | MISRA C:2012 Guidelines and Critical Safety Constraints | Refactor raw pointer operations to conform to safe MISRA rules | 2026-07-30 | Not Started | 2.222% | Pending
Day 45 | Phase 9: Concurrency & MISRA C | Systems Profiling, Leak Audits, and Graduate Code Review | Trace execution performance using gprof and debug leaks with Valgrind | 2026-07-31 | Not Started | 2.222% | Pending